## Tasks
id | task | description | assignee | duration | predecessors | start_date | end_date
discovery | Project discovery |  | Maya | 2 |  | 2026-01-05 | 2026-01-06
requirements | Requirements analysis |  | Alex | 3 | Project discovery | 2026-01-07 | 2026-01-09
ux-research | UX research |  | Nina | 2 | Project discovery | 2026-01-07 | 2026-01-08
ui-design | UI design |  | Nina | 4 | UX research | 2026-01-09 | 2026-01-12
backend-api | Backend API |  | Ivan | 5 | Requirements analysis | 2026-01-10 | 2026-01-14
frontend-dev | Frontend development |  | Olga | 5 | UI design | 2026-01-13 | 2026-01-17
integration | Integration |  | Ivan | 3 | Backend API;Frontend development | 2026-01-18 | 2026-01-20
qa-testing | QA testing |  | Alex | 3 | Integration | 2026-01-21 | 2026-01-23
production-release | Production release |  | Maya | 1 | QA testing | 2026-01-24 | 2026-01-24